## Sheet1
Gantt Chart 28/10 - 4/11 |  |  |  | Wednesday 28/10/14 | [10 empty] | Friday 30/10/15 | [5 empty] | Wednesday 04/11/15
|  |  |  | Period 1 |  |  |  |  | Period 2 | [5 empty] | Period 3 | [5 empty] | Period 4 |  |  |  |  | Period 5
Task Name | Roles | Duration | Predecessor | 9:00 | 9:10 | 9:20 | 9:30 | 9:40 | 9:50 | 10:00 | 10:10 | 10:20 | 10:30 | 10:40 | 2:25 | 2:35 | 2:45 | 2:55 | 3:05 | 3:15 | 11:05 | 11:15 | 11:25 | 11:35 | 11:45 | 11:55 | 12:05 | 12:15 | 12:25 | 12:35 | 12:45
Assign Roles | Matt | 10 Mins | Start Project | bar: Period 1 9:00
Make Repository | Matt | 10 Mins | Assign Roles | bar: Period 1 9:10
Add Collaberators | Matt | 10 Mins | Assign Roles | bar: Period 1 9:10
Plan Website Design | Cam/Sean | 20 Mins | Add Collaberators | bar: Period 1 9:20 to Period 1 9:30
Enter Data on SpreadSheet | Matt | 80 Mins | Add Collaberators | bar: Period 1 9:20 to Period 2 10:30
Create Website | Cam | 140 Mins | Plan Website Design | bar: Period 1 9:40 to Period 4 11:05
Design CSS | Cam | 40 Mins | Create Website | bar: Period 4 11:15 to Period 5 12:35
Design Brochure | Pat | 40 Mins | Add Collaberators | bar: Period 1 9:40 to Period 2 10:10
Create Brochure | Pat | 90 Mins | Design Brochure | bar: Period 2 10:20 to Period 3 3:15
Design C# Program | Sean/Matt | 60 Mins | Enter Data on SpreadSheet | bar: Period 3 2:25 to Period 3 3:15
Make C# Program | Sean/Matt | 90 Mins | Design C# Program | bar: Period 4 11:05 to Period 5 12:25
Finishing Touches | All | 20 Mins | All Events | bar: Period 5 12:35 to Period 5 12:45